## Slide 1
WA4 meeting
28th October 2014

## Slide 2
AGENDA
Introduction
  Approval last meeting minutes
WP41: Actions carried out since the last meeting. Next actions
  DESSIN website: status and internal area and other issues
  Target audience analysis and exploitation strategy. DRAFT Milestone!
  Newsletter: NOVEMBER Milestone!
  Establishment of demo-sites as showcases: coming actions
3. WP42: Actions carried out since the last meeting. Next actions
  Questionnaires and/or meetings with each SME and technology developer. status Milestone!
  Project implementation Plan «DESSIN product and technology promotion»
4. Any other issues
5. Next WA4 meeting: to be scheduled (proposal: 2nd December 10:00)

## Slide 3
1. WP41: Actions carried out since the last meeting. Next actions
T41.2  Website
Interactive private area  update Lisa
List of upcoming events: website & newsletter  DONE
Networking with other EU projects  identification DONE. Next actions?
Other issues?
MILESTONE MS8 “Target audience analysis and exploitation strategy” (M6)
T41.3  Public correspondence
Newsletter: 2nd newsletter to be sent in November 2014. Contents requested: deadline 4th November.
Annual Magazine: Under preparation, to be sent in January 2015. Contents will be requested before 28th November.
Factsheet: Under preparation, to be sent to all the project partners in January 2015.

## Slide 4
1. WP41: Actions carried out since the last meeting. Next actions
T41.4  DEMO SITES AS SHOWCASES
Brainstorming WA3
Make an inventory of existing ‘showcases’ and see what they offer and how they organised.
  Example: EIP Water  http://www.eip-water.eu/water-innovations-netherlandspdf
WP leaders will think further about opportunities to set up their demonstrations as showcases. This issue will also be discussed during the next WA3 meeting.

## Slide 5
2. WP42: Actions carried out since the last meeting. Next actions
T42.1  Market analysis reports
Feedback questionnaires
Update of matrix development
MILESTONE MS9 “Individual meeting with each SME and technology developer of DESSIN” (M6)
T42.2  Commercialization process maturity models (STARTED?)
T42.3  Business environment report
Project implementation Plan «DESSIN product and technology promotion»
  New version?
  Content distribution: Adelphi + CETaqua + IWW
T42.4  Support ESS lobbying for efficient modes of governance and finance
T42.5  Promotion of ESS assessment
  List of EU projects identified
  Other actions?