## Slide 1
WA2 - WA3 coordination meeting

## Slide 2: WA2 - WA3 coordination meeting ! 16th and 17th March 2016
WELCOME

## Slide 3
Agenda - DAY ONE – WA2 & WA3 coordination
10:00 - 10:05 – Welcome (David Schwesig (IWW))
10:05 - 10:15 – Introduction to the workshop (Rita Ugarelli (SINTEF), Gerard van den Berg (KWR))
10:15 - 12:30 – WA2 and WA3 presentations (20 min each):
11:15 - 11:50 – Coffee Break
12:30 - 13:15 – Lunch
13:15 - 14:00 – MIKE CUSTOMISED Software (Niels Riegels, DHI)
14:00 - 14:10 – Short Break
14:10 - 15:40 – Showcases
  14:10 - 14:20: Introduction about the showcases value in DESSIN (Gerard van den Berg (KWR))
  14:20 - 15:10: Activities for each showcases (10 min per demo site): Emscher, Hoffselva, Westland, Athens, Llobregat.
  15:10 - 15:40 - discussion
15:40 - 16:00 – Wrap up.
16:00 - 18:30 – Opportunity for targeted bilateral meetings on specific tasks.
16:00 - 17:00 – WAMT meeting
19:00 - Social dinner at Restaurant

## Slide 4
Agenda - DAY TWO – Excursion + Coordination of WA1 and WA3
8:15-13:15 – Excursion
08:15 - Gather at KWR office
08:30 - Stop at hotel
08:30 - 10:00 - Bus travel to Westland
10:00 – 10:15 - Coffee/tea
10:15 - 10:20 - Introduction Prominent (organization, water supply)
10:20 - 10:30 - Presentation Bruine de Bruin (organization, role in agricultural water supply)
10:30 - 11:00 - Backgrounds on the Westland demo site (Koen Zuurbier, KWR)
11:00 - 12:15 - Guided tour Westland site and facilities
12:15 - 13:15 - Transfer to KWR office
13:15 - 14:00 – Lunch and refreshing
14:00 - 16:00 – DESSIN ESS Evaluation Framework
14:00 - 14:30 - Update and overview of the final draft ESS Evaluation Framework + Sustainability Assessment and their application (Gerardo Anzaldúa and Clemens Strehl)
14:30 - 15:15 - Results of applying the framework on the mature sites (15min per site owner)
15:15 - 16:00 - Break-out groups for specific Q&A from demo sites to WA1 members
16:00 - 16:15 - Wrapping up and end of the meeting

## Slide 5
GOALs of the workshop
Meet: WA2 and WA3 partners will present the main outcomes of their work so far and the way forward – highlight the established collaboration with other demo sites - experiences with ESS framework - share with the audience the plans for the showcases!
Learn: the DESSIN ESS Evaluation Framework presented together + feedback from the mature sites on the application experience; MIKE CUSTOMISED Software the current status and plans for implementation anticipated in preparation to the DHI course in April for some of us!
Solve: discuss and plan how to collaborate on foreseen deviations
See: Guided tour Westland site and facilities
Enjoy: network and socialize

## Slide 6
WA2 status
Del. No. | Deliverable Name | WP No. | Delivery Date | Responsible | Status or MGT measures
23.1 | System requirement specification and system design documents | 23 | 31.08.2015 | DHI | late by 9 months - depending on D11.2
22.5 | Software for the evaluation of groundwater and surface water interactions | 22 | 31.08.2015 | Amphos21 | will be late but no negative impact on other project activities.
22.3 | Assessment Reversed Osmosis membrane clogging by varying redox conditions | 22 | 31.12.2015 | KWR | part I ready, part II under QA, ready by mid March 2016
23.2 | Windows installer that can be used to install the software | 23 | 30.04.2016 | DHI | will be late by 6 month - depending on D11.2
23.3 | User guides and system documentation | 23 | 31.05.2016 | DHI | will be late by 6 month - depending on D11.2
21.2 | Validated additional functions for the ADESBA planning tool | 21 | 31.12.2016 | SEGNO | 
21.3 | Technical conclusions from testing during site specific development and specifications for final designs | 21 | 31.12.2016 | INRIGO | 
The work is progressing smoothly
- 4 Deliverables submitted (D21.1 (UFT), D22.1(NTUA), D22.2 (NTUA), D22.4 (CETaqua))
- Adjustment of Deliverables for WP23 to align to WA1 and some minor delays in WP22)

## Slide 7
WA3 status
Del. No. | Deliverable Name | WP No. | Delivery Date | Responsible
31.1 | Conclusions from successful demonstration, and specifications for final design | 31 | 30.06.2017 | EG
31.2 | Final evaluation of the technological solution in terms of ESS and sustainability | 31 | 30.06.2017 | EG
32.1 | Design criteria and documentation of performance for local CSO overflow treatment | 32 | 30.06.2017 | INRIGO
32.2 | Conclusions from the demonstrations with projected effects on water quality, ESS, sustainability | 32 | 30.06.2017 | SINTEF
33.1 | Valorisation and demonstration of an ASR/RO application | 33 | 31.12.2017 | KWR
33.2 | Evaluation of the improvement of Ecosystem Services as a result of ASR/RO application | 33 | 31.12.2017 | KWR
34.3 | Evaluation and guidelines and recommendations for transfer to other Water Scarcity sites | 34 | 31.12.2017 | NTUA
35.1 | Evaluation of the results and impacts on ESS of a flexible ASR system and recommendations for transfer | 35 | 31.12.2017 | CETaqua
35.2 | Economic analysis and proposed payment regulation of the identified ecosystem services | 35 | 31.12.2017 | Amphos21
The work is progressing according to plan, no major delays)
- 1 Deliverable submitted (D34.1 (Chemitec))
- 4 Milestones submitted (MS19 (INRIGO), MS20 (KWR), MS22 (UFT), MS24 (EYDAP), MS28 (UFT, delayed)