## WAMT Tasks
DESSIN - Work Area Management Team Tasks
Meeting | What? | Who? | Until when? | Status (x = done) or comments
01-2014 | Organise next WAMT TelCo | Coordinator | 2014-03-03 | x
2014-01 | Fix date & venue for next WAMT face-to-face meeting in Oct/Nov 2014 | Coordinator | 2014-05-07 | x
2014-03 | Clarify need for and nature of QA measures for MS3, report to Coordinator | WA1 leader | 2014-04-02 | x
2014-03 | Clarify need for and nature of QA measures for MS4 & MS5, report to Coord. | WA2 leader | 2014-04-02 | x
2014-03 | Ask WP leaders within WA3 to include planning with regard to local stakeholder groups in their detailed work plan | WA3 leader | 2014-04-02 | x
2014-03 | Circulate project standard presentation & templates for minutes & deliverables | WA4 leader | 2014-03-07 | x
2014-03 | Provide WAMT team with latest version of DESSIN contact/mailing list | Coordinator | 2014-03-06 | x
2014-03 | Distribute within WAMT the WP42 presentation of services offered to SMEs | WA4 leader | 2014-03-22 | x
2014-03 | Cf. WAMT Decision #3: fwd list of critical points to Coordinator | WA3 leader | 2014-04-02 | x
2014-03 | Cf. WAMT Decision #5: clarify structure and access rights of internal website area | Coordinator | 2014-04-02 | x
2014-03 | Cf. WAMT Decision #6: take next steps to prepare request for GA amendment | Coordinator | 2014-04-02 | x
2014-04 | Inform adelphi about presentation and questionnaire (cf WAMT Decision #8) | WA4 leader | 2014-04-04 | x
2014-04 | Prepare template for monthly survey about events, publications, presentations | WA4 leader | 2014-05-07 | x
2014-05 | Re-send template for listing events (pre-filled with what is available so far) | WA4 leader | 2014-05-23 | x
2014-05 | Propose structure for internal website area | Coordinator | 2014-05-23 | x
2014-05 | Report on status of WP42 presentation and feedback from SMEs | WA4 leader | 2014-06-04 | postponed to 3 September '14
2014-05 | “developing demo sites into showcases”: draft definition and outline first steps | T41.4 lead KWR | 2014-06-04 | x
2014-06 | Get in touch with WA1 leader about link to EIP ESE | Coordinator | 2014-06-30 | x
2014-06 | Check status and activity level of local stakeholder groups | WA3 leader | 2014-12-21
2014-06 | Instruct all partners about internal website area and file exchange server | Coordinator | 2014-06-06 | x
2014-06 | Assign reviewer to D42.3 | WA4 leader | 2014-06-30 | x
2014-06 | Start preparation of joint WA2/3/WAMT meeting | WA3 leader | 2014-09-03 | x
2014-09 | Check mode of collaboration with EIP AG ESE | Coordinator | 2014-09-30 | x
2014-09 | Check necessary steps to finalise D11.1 with WP leader and report back to WA1 leader | Coordinator | 2014-09-22 | x
2014-09 | Provide Coordinator with a short list of documents drafted in WA1 and exchanged with EIP | WA1 leader | 2014-09-12 | x
2014-09 | Decide about MS3: formal review/QA procedure needed | WA1 leader | 2014-09-19 | x
2014-09 | Send "save the date" e-mail to all partners (about Athens event) | Coordinator | 2014-09-12 | x
2014-09 | Finalise meeting agenda, programme, invitation, info on logistics etc., and fwd to David for distribution | WA2 & WA3 lead | 2014-09-19 | x
2014-10 | Update Athens agenda according to decisions at WAMT 10/2014 | WA2 leader | 2014-10-20 | x
2014-10 | Contact WP leaders of WA3 and organise speakers for Athens event | WA3 leader | 2014-10-20 | x
2014-10 | Send reminder about registration for Athens event & option for bilateral meetings | Coordinator | 2014-10-01 | x
2014-10 | Inform WP42 partners about slot on 3 Nov | Coordinator | 2014-10-01 | x
2014-10 | Prepare background document about ESS valuation framework prior to Athens | WA1 leader | 2014-10-20 | x
2014-12 | submit D11.1, put to internal area, drop note informing all partners | Coordinator | 2014-12-03 | x
2014-12 | Ask D11.1 coauthors for consent to share document with ESE AG | WA1 leader | 2014-12-03
2014-12 | Inform WP leaders of WA3 about forthcoming exercise on ESS typology | WA1 leader | 2014-12-12
2014-12 | Sent MS7 to David | WA2 leader | 2014-12-05
2014-12 | Monitor completion of D34.1, report in case of problems/delay | WA3 leader | 2014-12-19 | done. Delayed until Feb 2015
2014-12 | Check status of other WP42 items and report in case of problems/delay | WA4 leader | 2014-12-05
x

## WAMT Decisions
DESSIN - Work Area Management Team Decisions
Meeting | Decision No. | What was decided? | Follow-up actions needed?
2014-01 | #1 | Monthly WAMT TelCos will take place on each 1st Wednesday of a month, 10-11 am. | to be organised by David
2014-03 | #2 | WP42 presentation of services offered to SMEs will be discussed (for approval) before release | completed
2014-03 | #3 | Analysis of critical points: a list of critical points (e.g. bottlenecks in RTD that may have an impact on demo activities) is currently being developed between WA2 and WA3. This will be included into the project management tool [“DESSIN WAMT Data and Tasks”] to enable monitoring by the WAMT. | check monthly
2014-03 | #4 | Quality Assurance of milestones: it is the WA leaders’ responsibility to decide (on a case-by-case basis) about the required level of documentation and QA. The decision (formal document or not, assigned reviewers [if any] and status of the milestone [e.g. “achieved and accepted on date xx.yy.zz”]) will be communicated by the responsible WA leader to the coordinator and recorded in the project management file [“DESSIN WAMT Data and Tasks”] to enable progress monitoring by the WAMT.
2014-03 | #5 | Availability of internal documents: as a general rule, internal documents should be accessible to all partners (if no matters of confidentiality are concerned). Examples of internal documents accessible to all are a) the detailed work plans developed within most WPs, b) Minutes of meetings like the WAMT, plus related files like the project management file “DESSIN WAMT Data and Tasks”, c) Milestone documents. | cf. task list of WAMT 2014-03
2014-03 | #6 | The WAMT approves Coordinator’s suggestion to go for an amendment of the Grant Agreement in order to include SINTEF Energi AS as 3rd party (linked to beneficiary Stiftelsen SINTEF) under special clause 10. Next step is to work out the request in detail and to ask for approval of all DESSIN beneficiaries to start the process with the Commission Services. This will have no effect on tasks & budget of any partner, but is needed to enable the SINTEF group to carry out the work as planned and defined in the DoW. | completed
2014-04 | #7 | There will be a monthly survey among the WA leaders (before each TelCo) about publications, events, presentations from DESSIN. | check monthly
2014-04 | #8 | The WP42 presentation is fine. Shouldn’t be send to the SMEs without an accompanying E-mail explaining the next steps. Questionnaire needs to be pre-filled with information about the SMES already available from proposal stage. | completed
2014-05 | #9 | Achievement of WA3 milestones will be documented by news items at the website. No formal documents.
2014-05 | #10 | WA leaders will go through the activities (e.g. at the demo sites) on a regular basis (e.g. monthly) and drop a few lines to WA4 about activities worth a blog entry (e.g. new well drilled…). | check monthly
2014-06 | #11 | There will be a joint WA2/WA3 meeting in November, back-to-back with a WAMT face-to-face. No WAMT TelCos in July/August (summer break). | completed
2014-09 | #12 | Joint event Athens will have 2 objectives: i) exchange WA2 and WA3; ii) first presentation of ESS valuation framework by WA1. All DESSIN partners will be invited. | completed
2014-09 | #13 | October TelCo will focus on preparation of the Athens Event | completed
x

## Deliverables
DESSIN - Deliverables
Del. No. | Deliverable Name | WP No. | Nature | Dissem. Level | Delivery Month | Delivery Date | Responsible | At least two reviewers: Can be from the same WA, but one needs to be from another organisation than the one responsible for the deliverable |  | Status or MGT measures | QA Measures
41.1 | Project branding (logo and templates) | 41 | O | PU | 3 | 2014-03-31 | CETaqua | WA leaders | WA leaders | submitted 31-03-14 | Participation in selection of logotype, validation of final version and templates
41.2 | Official Website launch | 41 | O | PU | 3 | 2014-03-31 | IWW | David | Laura/Marta | submitted 31-03-14 | Review of published contents, features and menus
11.1 | Internal state of the art report on ecosystem service evaluation regarding the items water status related changes in ESS, economic valuation and sustainability assessment of ESS | 11 | R | CO | 9 | 2014-09-30 | IWW | see column M | see column M | submitted 03-12-14 | Document is more of a milestone nature (intermediate step towards the final framework); hence it was agreed to have a comprehensive internal review only (involving all co-authors)
42.3 | Two business environment (outside-in) reports a) Scarcity b) Quality / WFD | 42 | R | RE | 10 | 2014-10-31 | Adelphi | David + Zenit | Gerardo Anzaldua | under QA | Review of the report
21.1 | Treatment units and instrumentation for CSO treatment solutions | 21 | P | CO | 12 | 2014-12-31 | UFT |  |  | under control, in time
22.1 | Guidelines for packaged plant selection and optimisation (report) | 22 | R | PU | 12 | 2014-12-31 | NTUA |  |  | under control, in time
34.1 | An optimal configuration small packaged plant for urban sewer mining | 34 | D | PU | 12 | 2014-12-31 | CHEMITEC |  |  | slightly delayed to Feb 15
42.1 | Market analysis (inside-out) for ESS software and solution packages | 42 | R | RE | 12 | 2014-12-31 | Adelphi | CETaqua | KWR | under control, in time | Review of the report
42.5 | M+E system for innovation and continuous monitoring of framework conditions and outcomes | 42 | D | PU | 12 | 2014-12-31 | Adelphi | David + Zenit | KWR | under control, in time | Review of the report
12.1 | Report on governance regime factors conducive to innovation uptake | 12 | R | PU | 14 | 2015-02-28 | KWR
12.2 | Report on financing approaches conducive to water sector innovation | 12 | R | PU | 14 | 2015-02-28 | CETaqua
12.3 | Manual for practitioners and policy makers on enabling factors, best practices and constraints to uptake of innovative measures | 12 | R | PU | 18 | 2015-06-30 | ECOLOGIC
51.1 | Scientific part of the first periodic report | 51 | R | RE* | 18 | 2015-06-30 | IWW
52.1 | Management and financial part of the first periodic report | 52 | R | CO | 18 | 2015-06-30 | IWW
23.1 | System requirement specification and system design documents | 23 | R | PU | 20 | 2015-08-31 | DHI
22.4 | Evaluation of pre-potable water requirements for safe injection into the aquifer through ASR | 22 | R | PU | 20 | 2015-08-31 | CETaqua
22.5 | Software for the evaluation of groundwater and surface water interactions | 22 | O | PU | 20 | 2015-08-31 | Amphos21
34.2 | A demonstrated intelligent software-hardware platform for monitoring and control of small packaged plants for urban sewer mining | 34 | O | PU | 24 | 2015-12-31 | TELINT
13.1 | Quantified ESS for 3 mature sites including recommendations for application | 13 | R | PU | 24 | 2015-12-31 | EG
22.2 | ICT platform for distributed sewer mining (technology) | 22 | P | PU | 24 | 2015-12-31 | NTUA
11.2 | Framework for evaluating changes in ecosystem services, including feedback from practical evaluation | 11 | R | PU | 24 | 2015-12-31 | ECOLOGIC
22.3 | Assessment Reversed Osmosis membrane clogging by varying redox conditions | 22 | R | PU | 24 | 2015-12-31 | KWR
23.2 | Windows installer that can be used to install the software | 23 | P | CO | 28 | 2016-04-30 | DHI
23.3 | User guides and system documentation | 23 | R | PU | 29 | 2016-05-31 | DHI
21.2 | Validated additional functions for the ADESBA planning tool | 21 | P | CO | 36 | 2016-12-31 | SEGNO
21.3 | Technical conclusions from testing during site specific development and specifications for final designs | 21 | R | CO | 36 | 2016-12-31 | INRIGO
41.4 | Established showcases at the five demo sites | 41 | D | PU | 36 | 2016-12-31 | KWR
51.2 | Scientific part of the second periodic report | 51 | R | RE* | 36 | 2016-12-31 | IWW
52.2 | Management and financial part of the second periodic report | 52 | R | CO | 36 | 2016-12-31 | IWW
31.1 | Conclusions from successful demonstration, and specifications for final design | 31 | R | PU | 42 | 2017-06-30 | EG
31.2 | Final evaluation of the technological solution in terms of ESS and sustainability | 31 | R | PU | 42 | 2017-06-30 | EG
32.1 | Design criteria and documentation of performance for local CSO overflow treatment | 32 | R | PU | 42 | 2017-06-30 | INRIGO
32.2 | Conclusions from the demonstrations with projected effects on water quality, ESS, sustainability | 32 | O, (seminar at VAV) | PU | 42 | 2017-06-30 | SINTEF
33.1 | Valorisation and demonstration of an ASR/RO application | 33 | D | PU | 48 | 2017-12-31 | KWR
33.2 | Evaluation of the improvement of Ecosystem Services as a result of ASR/RO application | 33 | R | PU | 48 | 2017-12-31 | KWR
34.3 | Evaluation and guidelines and recommendations for transfer to other Water Scarcity sites | 34 | R | PU | 48 | 2017-12-31 | NTUA
35.1 | Evaluation of the results and impacts on ESS of a flexible ASR system and recommendations for transfer | 35 | R | PU | 48 | 2017-12-31 | CETaqua
35.2 | Economic analysis and proposed payment regulation of the identified ecosystem services | 35 | R | PU | 48 | 2017-12-31 | Amphos21
41.3 | Content for dissemination and promotional material including a policy brief, a video and re-usable illustrations | 41 | R | PU | 48 | 2017-12-31 | CETaqua | IWW (Lisa) | Adelphi |  | Review of communication package (zip file) and report on actions carried out
42.2 | Sample Commercialization Process Maturity Models and capacity building on strategies for SMEs | 42 | O | RE | 48 | 2017-12-31 | Adelphi | CETaqua | David + Zenit |  | Review of the report
51.3 | Scientific part of the final report | 51 | R | RE* | 48 | 2017-12-31 | IWW
52.3 | Management and financial part of the final report | 52 | R | CO | 48 | 2017-12-31 | IWW
42.4 | Recommendations from the open ESS channels: European platforms, Roundtables, Conferences and Web platform | 42 | D | PU | 48 | 2017-12-31 | Adelphi | David | CETaqua |  | Review of the report
Formulas:
Delivery Date = EOMONTH(DATE(2013,12,12),[Delivery Month])
Note on H49: David Schwesig: intermediate version at M30

## Milestones
DESSIN - Milestones
MS No. | Milestone Name | WP | Delivery Month | Means of verification | Delivery Date | Responsible | Two Reviewers: Can be from the same WA, but one needs to be from another organisation than the one responsible for the deliverable |  | Formal document (Y/N) | Status or MGT measures | QA Measures
1 | Kick-off meeting | 51, 52 | 1 | Meeting held, minutes available. | 2014-01-31 | IWW | none | none | N | achieved
2 | Logo and applications are designed | 41 | 3 | A book of style is shared to all the partners and the logo and templates are used in all the materials produced | 2014-03-31 | CETaqua | CETaqua internal | CETaqua internal | D41.1 | achieved | Sending final version to WAMT for validation
3 | Analytical framework for governance regime assessments | 12 | 4 | Internal draft report outlining key elements of the review | 2014-04-30 | ECOLOGIC | none | none | Y, internal | achieved | 3 internal iterations involving all WP members
4 | Concept for the model setup of cross-current lamella settlers | 21 | 4 | Internal project memo by UFT with description of the construction tasks. | 2014-04-30 | UFT | Herman Helness | Doris Steinriede | Y, internal | achieved
5 | Design of HRF solution for pilot testing | 21 | 4 | Internal project memo by INRIGO with description of the design and plan for laboratory testing. | 2014-04-30 | INRIGO | Herman Helness | Gaute Moldestad | Y, internal | achieved
6 | Blog and Social networks are set up and first content is provided | 41 | 4 | The blog is online and the channels in different social networks are available and with content | 2014-04-30 | IWW | David | CETaqua | N | achieved | check existence of DESSIN profile in social networks
7 | Concept for optimized encapsulated ADESBA modules | 21 | 6 | Internal project memo by SEGNO with description of the design for the ADESBA modules. | 2014-06-30 | SEGNO |  |  |  | ready, to be sent to David by Herman
8 | Target audience analysis and exploitation strategy | 41 | 6 | First version available online | 2014-06-30 | IWW | CETaqua | adelphi | Y, internal | draft available - online | to be further elaborated (next step: David)
9 | Individual meeting with each SME’s and technology developer of DESSIN to identify potential intern networking and specific market needs | 42 | 6 | Internal minutes of the meetings | 2014-06-30 | adelphi | CETaqua |  |  | unknown | Check list of the meetings and 2 examples of minutes
10 | First newsletter published | 41 | 6 | All the contacts receive the electronic newsletter by e-mail and it is published in the website | 2014-06-30 | CETaqua | IWW Lisa | adelphi | Y, external | achieved | Review of draft before publication
11 | Mode of collaboration with EIP Water clarified | 51 | 6 | either to link up with action group ESE or to apply as an own action group | 2014-06-30 | IWW |  |  | N | discussed at WAMT and decided that we'll continue collaboration
12 | First version of evaluation methodology available for testing at mature sites | 11 | 12 | Mature case study leaders receive a copy of the evaluation framework report | 2014-12-31 | ECOLOGIC |  |  |  |  | will be slightly delayes (1st quarter of 2015)
13 | Completed integrated system architecture design | 22 | 12 | System architecture design completed and described | 2014-12-31 | NTUA
14 | Instrumentation and monitoring equipment installed | 21 | 12 | Instrumentation installed in demonstration units, tested and functioning flawlessly by LKI. | 2014-12-31 | LKI
15 | Completed evaluation of Freshkeeper benefits | 22 | 12 | Evaluation completed and benefits quantified | 2014-12-31 | KWR
16 | Selection of the most suitable pre-potable water and expected impacts | 22 | 12 | Selection completed and described | 2014-12-31 | CETaqua
17 | Formal presentation of DESSIN to the ESS European Roundtables and Platforms and establishment of action plans for fruitful interaction | 42 | 12 | and establishment of action plans for fruitful interaction | 2014-12-31 | adelphi | IWW Lisa |  |  |  | Check availability of text for news to be published in the website regarding the actions carried out
18 | Indicator system developed | 42 | 12 | first version in month 12, reviewed by month 25, finalised by month 48 | 2014-12-31 | adelphi | CETaqua |  |  |  | 2014 brief report on indicator system, 2015 & 2016 review of updated indicators
19 | Completed installation of high rate filter unit with monitoring instrumentation and data communication | 32 | 13 | Demonstration unit installed at demo site, tested and functioning flawlessly. | 2015-01-31 | INRIGO |  |  | N. News in the blog
20 | Completed installation of RO membranes | 33 | 16 | Installation completed and checked | 2015-04-30 | KWR
21 | Internal recommendations on the application of the ESS method | 13 | 18 | Internal project report outlining main recommendations/suggestions from case study leaders. | 2015-06-30 | EG
22 | Completed installation of full-scale cross-current lamella settlers | 31 | 18 | Installation completed | 2015-06-30 | UFT |  |  | N. News in the blog
24 | Completed installation of AMI-SM technologies | 34 | 18 | Installation completed and checked | 2015-06-30 | EYDAP
25 | First periodic report | 51, 52 | 18 | PSB approves first report for submission to EC | 2015-06-30 | IWW
26 | Applicability of evaluation methodology is tested and approved | 11, 13 | 21 | Internal project report including main recommendations/suggestions from case study leaders. | 2015-09-30 | SINTEF
27 | Implementation of web platform | 42 | 24 | The website is online and it has content | 2015-12-31 | adelphi | IWW Lisa |  |  |  | Check the web platform contents and menus
28 | Completed installation of container with cross-flow lamella settling unit | 32 | 25 | Demonstration unit installed at demo site, tested and functioning flawlessly. | 2016-01-31 | UFT |  |  | N. News in the blog
23 | Completed installation of full-scale RTC system | 31 | 30 | Installation completed | 2016-06-30 | SEGNO |  |  | N. News in the blog
29 | Completed installation of ASR pipelines | 35 | 30 | Installation completed | 2016-06-30 | CETaqua |  |  | N. News in the blog
30 | Identification of beneficial impacts and its role as ecosystem services | 35 | 30 | Beneficial impacts identified | 2016-06-30 | CETaqua
31 | Completed water quality monitoring and data gathering | 31 | 36 | Monitoring and data gathering completed | 2016-12-31 | EG |  |  | N. News in the blog
32 | Completed water quality monitoring and data gathering | 32 | 36 | Water quality sampling completed, samples analysed and quality verified. | 2016-12-31 | SINTEF |  |  | N. News in the blog
33 | Second periodic report | 51, 52 | 36 | PSB approves second report for submission to EC | 2016-12-31 | IWW
34 | Final report | 51, 52 | 48 | PSB approves final report for submission to EC | 2017-12-31 | IWW
Formulas:
Delivery Date = EOMONTH(DATE(2013,12,12),[Delivery Month])

## Critical Points
DESSIN - Critical Points
WP | Critical activity | Comment / measure
31,32,33,34,35, | Activities in WA1, specifically assessment of ESS for technical solutions (WA3) | Nadine Gerner (Emschergenossenschaft) is active in both activities and will report back to WA3 group.
31,32,33,34,35, | Progress activities in WA2 is critical for the demonstrations. | In most cases WA3 contacts are also involved in WA2 activities. In addition we plan to organize common WA2/WA3 meetings, starting with a face to face meeting later this year.
31 | Tasks T31.1-3 depend strongly on the completed work from other WPs, especially WP21 for the technological demonstrations (T31.1-2) and WA1 as well as WP23 for the ESS valuation (T31.3). The installation of the lamella settlers and the RTC at our mature sites depends on the approval of the operating service at the chosen facilities. For the installation of the container with the lamella settlers, no significant interferences with the normal operations, and therefore, no objections are expected. The RTC system, however, will drastically change/substitute the ongoing control systems, which might provoke concerns. The timely achievement of our milestones M31.1, in turn, is necessary to enable the subsequent installation and operation of the lamella settlers in WP32
32 | Completion of activities in WP21 (T21.1, T21.2, T21.3), active involvement of VAV Oslo
33 | nothing specifically yet
34 | nothing specifically yet
35 | Prepare the demonstration with enough time to inform local stakeholders. Invite all the related Demo site local stakeholders. Results achieved in T22.3.1 and T22.3.3 will be applied in the selection and design of the pre-treatment schemes to be tested in T3.5.1.

## Events
DESSIN - Critical Points
Start date | End date | Name of the Event, Country, Website… | Partners attending / organising / contact person | Expected contribution
25.6.14 | 26.6.14 | 2nd edition of Water Innovation Europe 2014 to the theme ‘Water: Green tape or blue gold ?’ Organiser: WssTP Country: Brussels (Belgium) http://www.waterinnovationeurope.eu/ | General event related to water innovation in Europe | none / unknown
26.8.14 | 30.8.14 | 6th Annual International ESP (Ecosystem Services Partnership) Conference 2013 Coutry: Bali, Indonesia Organiser: International Society for Ecological Economics http://www.isecoeco.org/ecosystem-services-partnership-esp-conference/ | General event related to Ecosystem Services | none / unknown
8.9.14 | 10.9.14 | Second Iberian Groundwater Conference Organiser: UPV Country: Valencia, Spain 8 – 10 September http://iah.org/events | CETaqua (attending) A21 (organising / attending) Marta Hernández Personnel from A21 to be decided | DESSIN presentation: Barcelona demo site (Spanish)
11.9.14 | 11.9.14 | MAR – SAT expert workshop (not specific website) Organiser: MEKOROT Country: Israel http://demoware.eu/en/news-and-events/events/mar-sat-expert-workshop | A21 attending (Ester Vilanova) | none / unknown
24.9.14 | 26.9.14 | ASR workshop in the Conference: Deltas in times of Climate Change (Rotterdam) http://www.climatedeltaconference2014.org/ | CETaqua Attending: Pere Camprovín KWR Attending: Marcel Paalman | Participation in the workshop Subsurface storage and recovery (ASR) of fresh water in saline groundwater. Visit pilot location Westland. Participation in the scientific part on freshwater by Koen Zuurbier
20.10.14 | 21.10.14 | Final SCARCE International Conference: River conservation under water scarcity. Integration of water quantity and quality in Iberian Rivers under global change Organiser: CSIC Country: Tarragona, Spain http://www.scarceconsolider.es/publica/P000Main.php | General event related to Ecosystem Services | none / unknown